Summary of the context and overall objectives of the project (For the final period, include the conclusions of the action)

This section should include information on:

- What is the problem/issue being addressed?

- Why is it important for society?

- What are the overall objectives?

1st report

Astronomical observations have revealed that very large polycyclic aromatic hydrocarbons (so-called GRAND PAHs) exist in copious amounts in the interstellar medium (ISM). They contain up to 20% of the entire carbon budget in the Universe and as such need to be understood in terms of their origins (how they form) and their eventual fate (how they are destroyed). In the ISM they are processed by the interstellar ultraviolet radiation field that permeates the Universe and can thus refurbish the molecular complexity of the Universe with the breakdown products of their photo-processing.

The research question is closely tied in with one of the fundamental questions humanity has asked itself for centuries; what are the origins of life on Earth? Understanding the role that radiation interacts with one of the Universe's greatest carbon reservoirs is of great importance to knowing where the molecular complexity in the Universe is originated and replenished to seed organic molecules in bountiful amounts in nascent solar systems; providing the key ingredients for life to be ignited.

The overall objective of this project is to measure the fragmentation pathways of very large polycyclic aromatic hydrocarbons (PAHs) in a laboratory setting by utilizing several complementary radiation techniques to gain a deeper understanding of the nature of GRAND PAHs and their overall role in the chemistry and physics of our Universe.

Work performed from the beginning of the project to the end of the period covered by the report and main results achieved so far (For the final period please include an overview of the results and their exploitation and dissemination)

1st report

The experimental apparatus used for the project is called the 'instrument for photodynamics of PAHs' or 'i-POP'. It is based in Leiden but is mobile and can be utilized in other large-scale radiation facilities around Europe such as Synchrotron SOLEIL in Paris and FELIX in Nijmegen. During the first and second week, an application for beam-time at the Synchrotron SOLEIL facility was written and submitted in collaboration with beamline scientists Laurent Nahon and Gustavo Garcia at the DESIRS beamline at SOLEIL.

During that same period, another beamtime application was written in collaboration with assistant professor Jordy Bouwman for beam-time at the Swiss Light Source synchrotron facility near Zurich. That application is going to focus on Nitrogen containing PAHs, also very relevant to the universal PAH budget and also relevant to PAH-containing soot particles that form in combustion processes.

For the past few weeks the laser system that is used in Leiden has been suffering from a few malfunctions. First, there was a connection problem between one of the delay generators and the computer where the data acquisition is monitored. This problem was fixed in the second week of September. Secondly, the laser spot size proved to be too small so the laser wasn't fragmenting enough molecules in i-POP's ion trap to obtain a decent signal. This problem was fixed in the third week of September by achieving an alignment with a larger spot size. This allowed a PhD student in our group to finish her measurements of the fragmentation patterns of the Coronene molecule (C24H12), an important molecule for this project as it serves as an important benchmark to the sort of small, symmetric PAH photodissociation that forms the basis of this proposal; building up to GRAND PAHs, which contain up to one hundred carbon atoms.

Concurrently to the laboratory measurements, I as well as prof. Linnartz and associate prof. Bouwman have been in contact with an in-house group in Leiden that specializes in organic syntheses or large PAHs for a collaborative opportunity. Large PAHs are difficult to synthesize and not easy to come by and so we have also been looking towards other options, e.g. in Germany for research groups interested in the properties of such large PAHs.

2nd report

In October I managed to successfully connect with a synthesis group in Mainz, Germany, who specialize in synthesizing very large PAH samples. We have started a mutually beneficial collaboration and they have supplied me with two samples of very large PAHs that will be used on i-POP.

The beamtime application to SOLEIL was accepted and hence a significant amount of preparatory work has now commenced. In order to successfully implement the setup at the SOLEIL synchrotron we need to bring a few adjustments that allow us to connect the i-POP chamber to the DESIRS beamline at SOLEIL. The beamtime is set in the beginning of April.

The beamtime application to the Swiss Light Source was also accepted and hence I will travel to Switzerland with Jordy Bouwman in February to measure the photoelectron spectra of a series of Nitrogen containing PAHs.

From the 1st report, there have been some more experimental hiccups with the i-POP setup and the latest has been the heating elements not behaving accordingly. This was recently solved as I found that there was a faulty connection that was leaking current that should have been going through the oven, inducing heating. This issue has now been solved.

I participated in beamtime at FELIX where the IRMPD spectrum of the dehydrogenated naphalene cation was measured. This is an ongoing collaboration between the Leiden group and FELIX and I was brought on the team for the experience as I plan to write my own FELIX beamtime application and carry out experiments there myself in the near future.

Regarding the coronene molecule mentioned in the 1st report, it turned out that more measurements were required and this delayed my own progress on i-POP but gave me more experience working with the dye laser which is requires a gentle approach due to his age. By assisting with alignment of the laser I helped finish the coronene fragmentation measurements.

I have now also almost finished the manuscript to a research paper focused on the photoionization dynamics of C60. This is a project that was initiated during my last postdoc in SOLEIL, but in collaboration with Prof. Linnartz, my current supervisor. The results are very interesting and I anticipate a significant impact on future theoretical models because the results imply that the theoretical models employed so far to explain the C60+ transitions that are responsible for the diffuse interstellar bands (DIBs), have started from slightly erroneous assumptions. This work has potential to impact not only DIBs research but also help constrain astrochemical models that include the photoionization of C60 as well as the electron kinetic energy distribution of the produced photoelectrons. This paper will hopefully be submitted soon and I intend on presenting its results to  the astrochemistry community at a conference in April.

I participated in beamtime at SOLEIL in December with Prof Martin Schwell from the LISA laboratory in Paris Est. The project was centered around the photoionization of astrobiologically interesting molecules and the beamtime was very successful with a series of spectra recorded which gave very intriguing results regarding the photoionization processes in these molecules.

I wrote with Martin an application for a CNRS position in his group that was submitted in the beginning of January, but his laboratory would be an ideal place for me as an extension of my research career upon the end of this Marie Curie Individual Fellowship.

3rd report

Before COVID-19

Experimental difficulties concerning i-POP unfortunately continued and halted its operation. As it turned out, the heating element inside the oven was damaged and the oven needed to be replaced. A new oven was ordered but this meant that i-POP could not be utilized for the SOLEIL beamtime scheduled in the beginning of April.

Thus, backup plans were put into play. At SOLEIL there is a preexisting ion trap which introduces PAHs into the trap via a nebulizer. For such an introduction into the trap the PAHs have to be soluble in organic solvents which the very large PAHs proposed for the beamtime are not. Thus a different approach is required and we decided to go with very large PAHs (including up to and including 96 carbon atoms) which have either been chlorinated (had Cl atoms attached to their edges rather than hydrogen atoms) or had large alkyl groups attached to them. The chlorination and alkylation distort the topography of the PAHs enough to make them soluble in toluene which makes them ideal candidates to study in the ion trap at the DESIRS beamline in SOLEIL. The PAH samples were provided by the group in Mainz which had previously sent samples of large PAHs for us to study with i-POP.

The February beamtime at the Swiss Light Source went a slightly different direction than originally anticipated. The original project concerning doubly nitrogenated PAHs was put on hold in favor of looking into the pyrolysis of resonantly stabilized radicals (RSRs) which are thought to be important reaction intermediates (or building blocks) of PAHs, both in space and in combustion. The measurement campaign turned out to be fraught with difficulties but still allowed us to record spectra that shine light on the role of the fulvenallenyl radical in thermal degradation of benzyl.

The aforementioned C60 manuscript was finished and submitted for publication. Currently I await the referee reports.

After COVID-19

After everything was put into lockdown, the upcoming SOLEIL run was cancelled as well the next FELIX run which was scheduled in May. This will obviously delay the output of the project by a significant amount of time as the SOLEIL and FELIX runs have to be rescheduled for a later unknown date.

No progress will be made in the laboratory for the time being so other means of obtaining data are being pursued.

I have started to learn to code with Python to become competent in implementing and using astrochemical codes to perform such calculations relevant to the chemistry of the interstellar medium that includes the formation and chemical roles of PAHs.

I have also started to learn graphical programming with Labview to be able to modify and adjust the current Labview programs used on i-POP and make data acquisition a lot more straight-forward and user-friendly to hasten the data acquisition – data treatment process.

I have also started to learn to perform quantum chemical calculations to be proficient in exploring potential energy surfaces, simulate spectra and locate transition states of reaction intermediates relevant to the photo-induced breakdown of PAHs.

In other words, I have started on a journey to become a lot more efficient, computationally speaking, in producing data complementary to the results obtained in the laboratory which can be done remotely.

As a side note, I still have results from my previous postdoc position which I have yet to write up in articles which include photoionization of astrophysically relevant molecules and the formation of benzene via the recombination of propargyl radicals.

Progress beyond the state of the art, expected results until the end of the project and potential impacts (including the socio-economic impact and the wider societal implications of the project so far)

1st report

The fragmentation patterns of the coronene molecule is an encouraging start to the project. It provides good momentum for future measurements and the analysis of the results will give a healthy benchmark for the data analyses of much larger molecules than coronene (GRAND PAHs which include up to and above one hundred carbon atoms). If the beamtime applications to SOLEIL and SLS will be accepted, the project will be furthered by including synchrotron radiation techniques to larger PAHs as well as nitrogen-including PAHs, thus expanding the scope of the projected results.

A lot more is to come, such as measurements campaigns at the FELIX laboratory in Nijmegen to record the breakdown of large PAHs with multi-photon infra-red absorption processes, further experimentation in Leiden with PAHs of increasing size and complexity, and a concrete dissemination program that will include both presentations of the results to the scientific (chemical and astronomical) community as well as outreach activities geared towards the general public.

2nd  report

With both the beamtime applications to SOLEIL and PSI accepted, the project looks to have a very healthy upcoming research output. Further results from the SOLEIL beamtime in December and another FELIX proposal accepted that I will collaborate on, the projected results are many and significant potential exists for state of the art results in the coming year.

3rd report

Now that the SOLEIL and FELIX beamtimes have been halted due to the outbreak of COVID-19, progress in that research direction is at a standstill. Instead, other avenues of complementary research are being pursued in terms of astrochemical modeling, quantum chemical calculations and developing a more user friendly graphical user interface for future data acquisitions.