Summary of the context and overall objectives of the project (For the final period, include the conclusions of the action)

This section should include information on:

- What is the problem/issue being addressed?

- Why is it important for society?

- What are the overall objectives?

1st report

Astronomical observations have revealed that very large polycyclic aromatic hydrocarbons (so-called GRAND PAHs) exist in copious amounts in the interstellar medium (ISM). They contain up to 20% of the entire carbon budget in the Universe and as such need to be understood in terms of their origins (how they form) and their eventual fate (how they are destroyed). In the ISM they are processed by the interstellar ultraviolet radiation field that permeates the Universe and can thus refurbish the molecular complexity of the Universe with the breakdown products of their photo-processing.

The research question is closely tied in with one of the fundamental questions humanity has asked itself for centuries; what are the origins of life on Earth? Understanding the role that radiation interacts with one of the Universe's greatest carbon reservoirs is of great importance to knowing where the molecular complexity in the Universe is originated and replenished to seed organic molecules in bountiful amounts in nascent solar systems; providing the key ingredients for life to be ignited.

The overall objective of this project is to measure the fragmentation pathways of very large polycyclic aromatic hydrocarbons (PAHs) in a laboratory setting by utilizing several complementary radiation techniques to gain a deeper understanding of the nature of GRAND PAHs and their overall role in the chemistry and physics of our Universe.

Final report – conclusions of the action

The conclusions for this action are quite significant. I have found that PAHs fragment in quite universal ways, i.e., no matter the size or shape of PAHs, their fragmentation products appear to be almost identical. This gives rise to particular fragments that could easily build up in the universe and act as carbon reservoirs before being inducted into nascent molecular clouds and eventually stars and planets. Perhaps more importantly, these fragments are very likely candidates to being the carriers of the elusive Diffuse Interstellar Bands (DIBs), which is a century old mystery yet to be solved. But, thanks to the results of this action, we now have a new methodology to finally uncover and solve the mystery of the DIBs.

Work performed from the beginning of the project to the end of the period covered by the report and main results achieved so far (For the final period please include an overview of the results and their exploitation and dissemination)

1st report

The experimental apparatus used for the project is called the 'instrument for photodynamics of PAHs' or 'i-POP'. It is based in Leiden but is mobile and can be utilized in other large-scale radiation facilities around Europe such as Synchrotron SOLEIL in Paris and FELIX in Nijmegen. During the first and second week, an application for beam-time at the Synchrotron SOLEIL facility was written and submitted in collaboration with beamline scientists Laurent Nahon and Gustavo Garcia at the DESIRS beamline at SOLEIL.

During that same period, another beamtime application was written in collaboration with assistant professor Jordy Bouwman for beam-time at the Swiss Light Source synchrotron facility near Zurich. That application is going to focus on Nitrogen containing PAHs, also very relevant to the universal PAH budget and also relevant to PAH-containing soot particles that form in combustion processes.

For the past few weeks the laser system that is used in Leiden has been suffering from a few malfunctions. First, there was a connection problem between one of the delay generators and the computer where the data acquisition is monitored. This problem was fixed in the second week of September. Secondly, the laser spot size proved to be too small so the laser wasn't fragmenting enough molecules in i-POP's ion trap to obtain a decent signal. This problem was fixed in the third week of September by achieving an alignment with a larger spot size. This allowed a PhD student in our group to finish her measurements of the fragmentation patterns of the Coronene molecule (C24H12), an important molecule for this project as it serves as an important benchmark to the sort of small, symmetric PAH photodissociation that forms the basis of this proposal; building up to GRAND PAHs, which contain up to one hundred carbon atoms.

Concurrently to the laboratory measurements, I as well as prof. Linnartz and associate prof. Bouwman have been in contact with an in-house group in Leiden that specializes in organic syntheses or large PAHs for a collaborative opportunity. Large PAHs are difficult to synthesize and not easy to come by and so we have also been looking towards other options, e.g. in Germany for research groups interested in the properties of such large PAHs.

2nd report

In October I managed to successfully connect with a synthesis group in Mainz, Germany, who specialize in synthesizing very large PAH samples. We have started a mutually beneficial collaboration and they have supplied me with two samples of very large PAHs that will be used on i-POP.

The beamtime application to SOLEIL was accepted and hence a significant amount of preparatory work has now commenced. In order to successfully implement the setup at the SOLEIL synchrotron we need to bring a few adjustments that allow us to connect the i-POP chamber to the DESIRS beamline at SOLEIL. The beamtime is set in the beginning of April.

The beamtime application to the Swiss Light Source was also accepted and hence I will travel to Switzerland with Jordy Bouwman in February to measure the photoelectron spectra of a series of Nitrogen containing PAHs.

From the 1st report, there have been some more experimental hiccups with the i-POP setup and the latest has been the heating elements not behaving accordingly. This was recently solved as I found that there was a faulty connection that was leaking current that should have been going through the oven, inducing heating. This issue has now been solved.

I participated in beamtime at FELIX where the IRMPD spectrum of the dehydrogenated naphalene cation was measured. This is an ongoing collaboration between the Leiden group and FELIX and I was brought on the team for the experience as I plan to write my own FELIX beamtime application and carry out experiments there myself in the near future.

Regarding the coronene molecule mentioned in the 1st report, it turned out that more measurements were required and this delayed my own progress on i-POP but gave me more experience working with the dye laser which is requires a gentle approach due to his age. By assisting with alignment of the laser I helped finish the coronene fragmentation measurements.

I have now also almost finished the manuscript to a research paper focused on the photoionization dynamics of C60. This is a project that was initiated during my last postdoc in SOLEIL, but in collaboration with Prof. Linnartz, my current supervisor. The results are very interesting and I anticipate a significant impact on future theoretical models because the results imply that the theoretical models employed so far to explain the C60+ transitions that are responsible for the diffuse interstellar bands (DIBs), have started from slightly erroneous assumptions. This work has potential to impact not only DIBs research but also help constrain astrochemical models that include the photoionization of C60 as well as the electron kinetic energy distribution of the produced photoelectrons. This paper will hopefully be submitted soon and I intend on presenting its results to  the astrochemistry community at a conference in April.

I participated in beamtime at SOLEIL in December with Prof Martin Schwell from the LISA laboratory in Paris Est. The project was centered around the photoionization of astrobiologically interesting molecules and the beamtime was very successful with a series of spectra recorded which gave very intriguing results regarding the photoionization processes in these molecules.

I wrote with Martin an application for a CNRS position in his group that was submitted in the beginning of January, but his laboratory would be an ideal place for me as an extension of my research career upon the end of this Marie Curie Individual Fellowship.

3rd report

Before COVID-19

Experimental difficulties concerning i-POP unfortunately continued and halted its operation. As it turned out, the heating element inside the oven was damaged and the oven needed to be replaced. A new oven was ordered but this meant that i-POP could not be utilized for the SOLEIL beamtime scheduled in the beginning of April.

Thus, backup plans were put into play. At SOLEIL there is a preexisting ion trap which introduces PAHs into the trap via a nebulizer. For such an introduction into the trap the PAHs have to be soluble in organic solvents which the very large PAHs proposed for the beamtime are not. Thus a different approach is required and we decided to go with very large PAHs (including up to and including 96 carbon atoms) which have either been chlorinated (had Cl atoms attached to their edges rather than hydrogen atoms) or had large alkyl groups attached to them. The chlorination and alkylation distort the topography of the PAHs enough to make them soluble in toluene which makes them ideal candidates to study in the ion trap at the DESIRS beamline in SOLEIL. The PAH samples were provided by the group in Mainz which had previously sent samples of large PAHs for us to study with i-POP.

The February beamtime at the Swiss Light Source went a slightly different direction than originally anticipated. The original project concerning doubly nitrogenated PAHs was put on hold in favor of looking into the pyrolysis of resonantly stabilized radicals (RSRs) which are thought to be important reaction intermediates (or building blocks) of PAHs, both in space and in combustion. The measurement campaign turned out to be fraught with difficulties but still allowed us to record spectra that shine light on the role of the fulvenallenyl radical in thermal degradation of benzyl.

The aforementioned C60 manuscript was finished and submitted for publication. Currently I await the referee reports.

After COVID-19

After everything was put into lockdown, the upcoming SOLEIL run was cancelled as well the next FELIX run which was scheduled in May. This will obviously delay the output of the project by a significant amount of time as the SOLEIL and FELIX runs have to be rescheduled for a later unknown date.

No progress will be made in the laboratory for the time being so other means of obtaining data are being pursued.

I have started to learn to code with Python to become competent in implementing and using astrochemical codes to perform such calculations relevant to the chemistry of the interstellar medium that includes the formation and chemical roles of PAHs.

I have also started to learn graphical programming with Labview to be able to modify and adjust the current Labview programs used on i-POP and make data acquisition a lot more straight-forward and user-friendly to hasten the data acquisition – data treatment process.

I have also started to learn to perform quantum chemical calculations to be proficient in exploring potential energy surfaces, simulate spectra and locate transition states of reaction intermediates relevant to the photo-induced breakdown of PAHs.

In other words, I have started on a journey to become a lot more efficient, computationally speaking, in producing data complementary to the results obtained in the laboratory which can be done remotely.

As a side note, I still have results from my previous postdoc position which I have yet to write up in articles which include photoionization of astrophysically relevant molecules and the formation of benzene via the recombination of propargyl radicals.

4th report

Since the last report, some significant progress has been made despite the difficult conditions surrounding the COVID-19 epidemic. This was made even harder with my partner getting sick shortly after the last report.

In terms of personal development, I partook in an astrochemistry course taught by Prof. Ewine van Dishoeck which was integral to me being able to contextualize my research in a more astrophysical setting. To capitalize on this, I continued working on a previous project with Prof Martin Schwell from the LISA laboratory at Université Paris Est, on the photoionization of methylketene, a molecule of astrophysical interest. From this project has emerged an article where I am second, but corresponding author and by putting the astrochemistry course to good use, I wrote a comprehensive astrochemical section in the article where the experimental findings are contextualized regarding the presence and eventual fate of methylketene in the interstellar medium. This article is at the time of writing in press.

The C60 manuscript was accepted for publication in PCCP and was chosen for the back cover of the issue. This was fantastic news and a personal highlight. The article has now been officially published.

As things in my home country (Iceland) started to open up, I took advantage of an offer to give a popular talk about astrochemistry for Nerdnite Reykjavík. Nerdnite is an international organization where speakers on a wide variety of subjects give talks in a local bar to a layman audience. Several dozens of people came to see my talk on “Chemical Weirdness in Space” which in Iceland is quite successful. The talk was recorded and is available on my website.

The project carried out in February on the Swiss Light Source has continued as well and the results have now been analyzed and will be summarized in a manuscript that is currently in progress.

Other previous projects from my postdoc have also been finished, one including the recording of threshold photoelectron spectra of several PAHs that were used to identify them as components in combustion experiments. This paper has been published in PCCP.

With spurious laboratory work now feasible. I have been taking advantage and calibrating the new oven that was ordered just before the COVID-19 lockdown. This takes quite some time, but it is important for the oven to properly function at a very wide temperature range considering the sizes of the PAHs I intend on studying. When the oven calibration is complete, several PAH samples will be optimized in the ion trap to optimize its performance. This will pave the way for more students to easily acclimate to the new setup and deliver results in a relatively short time.

5th report

The biggest change since the last report has been the opening of the Laboratory for Astrophysics which I have taken advantage of and made significant progress in the re-optimization procedure for i-POP.

The oven has now been calibrated up to above 500°C and is easily operable. I have implemented a comprehensive and systematic operating procedure towards obtaining good signals inside the ion trap which consists of: (i) Heating the oven incrementally and scanning over the RF amplitudes required for the PAH samples in question, (ii) scanning the electron gun energy and emission current to optimize the PAH parent signal, (iii) scanning the extraction delay and duration to further optimize the PAH parent signal, and (iv) finalize optimization by fine-tuning the phase and RF voltages to optimize the resolution and signal to noise ratio.

The laser used for fragmentation of the PAHs has been aligned as well and its power was measured to be on par with previous experiments. The re-optimized i-POP setup was used to obtain the laser-induced fragmentation pattern of coronene which may turn out to be complementary to the experiments that were finalized last November with my help.

A plan has been established to perform a series of experiments on PAHs of varying sizes and this will occupy my laboratory time for the next months.

In terms of personal development actions I have now been enrolled in several courses offered by Leiden university that will help develop my management and other soft skills. I am now half-way through a course focused on training PhD candidates and I have finished a course on giving and receiving feedback in an international context; both courses being extremely interesting and useful. Upcoming are further courses that include writing excellent grant proposals, blogging about research, networking skills for young scientists and basic management and leadership skills.

Regarding previous FELIX measurements I have touched base with Jos Oomens to carry out my secondment there next January and/or February and soon we will discuss what sorts of experiments I will be involved in and the process of submitting my own proposals for future beamtime to carry out my own experiments.

I have received an invitation to give a presentation of my work on C60+ at the next CHAINS meeting and this is will be my first invited lecture.

6th report

As the year 2020 is ending there are some very positive outcomes to report on.

I completed a series of measurements of the photo-induced breakdown on dicoronylene (C48H20) and the results are very interesting as they reveal some very interesting breakdown products which appear to be very stable. I expect these results to be published in 2021 but a few more measurements are required.

From the middle of November onwards I have been focusing on getting work done from home as I had several personal development courses to finish that included project management, Phd student supervision, networking for scientists, etc.

Additionally, an online beamtime at the Swiss Light Source was completed with Jordy Bouwman, working on two isomers comprising di-nitrogen substituted naphthalene PAHs, namely quinoxaline and quinozaline (C8N2H6). The results of this run will be analyzed early in the new year and published in 2021 as well as the results on the decomposition of the benzyl radical (C6H5-CH2), but that paper will soon be ready for submission.

I have also submitted several B.Sc. projects in hopes of testing my supervision skills in mentoring bright B.Sc. students interested in astrochemical research.

My first invited talk at the virtual CHAINS conference went extremely well and I got very nice feedback from everyone who saw it. Giving this talk further opened the doors for me to the EDIBLES consortium which is a group of astronomers, modellers and laboratory astrochemists who actively work on research related to the Diffuse Interstellar Bands (DIBs), and will allow me to position myself strongly within this community and actively work on assigning known DIBs to species observed in the laboratory such as C60+.

I also gave a virtual talk for the staff at the LISA laboratory in Paris which is my highest priority future job prospect. I have been in regular contact with Prof. Martin Schwell who wants to support me for a CNRS position in France and I am preparing a CNRS application under the working title “Pushing the Boundaries of Laboratory Astrochemistry”.

Next semester I will also be assisting with a course in statistics for astronomers which is going to be very beneficial to me for several reasons. Primarily, it will allow to put the computational skills in Python that I have started to work on during the pandemic into effect and cement my Python skills with emphasis on astronomical projects. This will undoubtedly open more doors for me in the future in terms of applying my skillset to astronomical projects.

7th report

During the first few months of 2021, there has been some good progress in the laboratory with the i-POP instrument. Breakdown mass spectra of PAHs such as Dicoronylene, Isoviolanthrene, and two dibenzo pyrene isomers have been recorded. There is a definite trend in breakdown products that is observed for all these PAHs indicative of a deeper universality of PAH fragmentation pattern. This has important implications for astrophysics as this provides definite clues about the nature of the carriers of the elusive diffuse interstellar bands (DIBs). Laboratory work will continue over the next couple of months with greater emphasis on larger PAH species, GRANDPAHs.

Because of an illness of one of the Phd students in the group, I was tasked with taking over a set of measurement campaigns at the FELIX laboratory in Nijmegen. The run focused on recording the IR spectra of singly- and doubly dehydrogenated PAH isomers, namely Phenanthrene and Anthracene. The results are striking as the recorded spectra appear to be the exact same, hinting at a common isomeric fragment that is already obtained by the loss of one and two H-atoms.

Secondly, I have initiated contact with a second group at FELIX to perform measurements on the GRANDPAH samples I obtained from the synthesis group in Mainz. The preliminary measurements that have been performed were done on chlorinated, alkylated and some pure GRANDPAH species. The objective was to find a direct link between the pure species and the chlorinated / alkylated species such that molecules that are more soluble in organic solvents can be used as a proxy to decipher spectroscopic information about GRANDPAHs that are notoriously difficult to isolate and measure in gaseous and other media. The preliminary results are promising and I intend on visiting FELIX again for an extended period of time for my secondment to learn more about the instrumentation, how to write FELIX proposals and the data analysis.

A proposal for the Hubble space telescope (HST) will be submitted this week in collaboration with members of the EDIBLES consortium. The proposal will focus on completing the dataset on the diffuse interstellar bands (DIBs) that have been assigned to the C60+ cation. If accepted, this would be my first observation campaign which I am very excited about.

This year I have attended two meetings and given a presentation on my C60+ photoionization results, namely at the American Physical Society (APS) virtual meeting (February 2021) and the American Chemical Society (ACS) virtual meeting (April 2021). In both cases my talks have been received very well and I have heard very positive feedback.

Unfortunately, the SOLEIL beamtime that I had scheduled for this March were postponed due to beamline technical issues. The beamtime will be rescheduled during the fall semester 2021, and I am currently awaiting the outcome of two SOLEIL proposals I submitted during the last SOLEIL call (February 2021).

Final report

In 2021, experiments have continued with the i-POP instrument. These include finishing work on a third dibenzopyrene isomer, dicoronylene, and isoviolanthrene. Experiments on C60H22 were attempted for a couple of months but unfortunately without success. The results from these measurements are currently being prepared for a series of publications, talks, and other outreach activities.

To combat the intrusive effects of academics’ career options, Leiden University offered contract extensions to postdoctoral researchers in exchange for some teaching obligations. I accepted this offer and was appointed as an assistant lecturer in a course entitled: “” which provides astronomy students with a comprehensive and highly utilizable background in statistical methodology and how it is utilized in astronomy and astrophysics. This was a great opportunity to build on my already existing teaching profile to include work on statistics and astronomy, but my background in spectroscopy turned out being commensurate to the course where I gave a lecture on spectral line profiles and how they are linked with statistical methodologies.

The FELIX measurements on Anthracene and Phenanthrene were carried out successfully in April and June (HRH: check) and these results are currently being analyzed by the PhD students whose health issues caused me to partake in the measurement campaign.

My main project concerning GRANDPAH samples provided by collaborators in Mainz was carried out over the course of the summer where we attempted to measure the IR spectra of several perchlorinated and alkylated PAHs. Some measurements were very successful but others were not. Currently, these results are being analyzed between myself and Dr. Julianna Palotás from the FELIX laboratory.

A bit of bad news was that our HST proposal to search for further signs of C60+ was rejected. The proposal made it to the first quintile which is better than the previous try which made it to the second quintile.

On the other hand, I have been inducted into the ARIEL consortium which is working on preparations for the upcoming ARIEL telescope which will be devoted to imaging and inspecting exoplanetary atmospheres.

Some more positive outcomes include a SOLEIL beamtime proposal that was accepted on the smallest aromatic hydrocarbon (c-C3H3+). This work will be carried out in late November and my previous beamtime that had to be rescheduled will be carried out in the beginning of October.

Finally, I was invited to give a presentation at the Journée de Spectroscopie Moléculaire (JSM) which was held in Rennes, France, in July.

For the final period please include an overview of the results and their exploitation and dissemination

i-POP

The work performed on i-POP has encompassed the fragmentation behavior of several astronomically relevant PAHs including three dibenzopyrene isomers, isoviolanthrene, and dicoronylene. More experiements are envisioned and will be performed under my supervision in the additional year I will spend in Leiden.

FELIX

The work performed at FELIX has included the recording the IR spectra of several perchlorinated and alkylated PAHs. These are currently being analyzed.

SOLEIL

Unfortunately, because of the COVID-19 pandemic, all measurement campaigns at SOLEIL had to be delayed. However, two beamtimes are scheduled in October and November 2021 to work on GRANDPAHs and c-C3H3, the smallest aromatic molecule in the universe.

SLS

I joined assistant professor J. Bouwman on two beamtime runs at the Swiss Light Source (SLS). The first saw us solve an old mystery involving phthalide pyrolysis and allowed us to clarify the role of important combustion intermediates (i.e. important intermediates involved in the interstellar and terrestrial formation of PAHs) such as fulveneallene, 1-, 2-, and 5-ethynyl cyclopentadiene, and fulveneallynyl.

Publications

There are multiple publications in preparation from the work performed during this action and will be published in the additional year I will spend in Leiden. Besides publications on my photoionization work involving C60 and phthalide pyrolysis, I actively published work on photoionization that I had led and participated in during my last position at the SOLEIL synchrotron.

Dissemination

I have been very active disseminating my work to the research community as evidenced by my participation in the virtual EAS conference in July 2020, the virtual APS meeting in February 2021, the virtual ACS meeting in March 2021, and my first two invited talks, first at the CHAINS meeting in December 2020 in the Netherlands and the Journées de Spectroscopie Moléculaire in France.

Progress beyond the state of the art, expected results until the end of the project and potential impacts (including the socio-economic impact and the wider societal implications of the project so far)

1st report

The fragmentation patterns of the coronene molecule is an encouraging start to the project. It provides good momentum for future measurements and the analysis of the results will give a healthy benchmark for the data analyses of much larger molecules than coronene (GRAND PAHs which include up to and above one hundred carbon atoms). If the beamtime applications to SOLEIL and SLS will be accepted, the project will be furthered by including synchrotron radiation techniques to larger PAHs as well as nitrogen-including PAHs, thus expanding the scope of the projected results.

A lot more is to come, such as measurements campaigns at the FELIX laboratory in Nijmegen to record the breakdown of large PAHs with multi-photon infra-red absorption processes, further experimentation in Leiden with PAHs of increasing size and complexity, and a concrete dissemination program that will include both presentations of the results to the scientific (chemical and astronomical) community as well as outreach activities geared towards the general public.

2nd  report

With both the beamtime applications to SOLEIL and PSI accepted, the project looks to have a very healthy upcoming research output. Further results from the SOLEIL beamtime in December and another FELIX proposal accepted that I will collaborate on, the projected results are many and significant potential exists for state of the art results in the coming year.

3rd report

Now that the SOLEIL and FELIX beamtimes have been halted due to the outbreak of COVID-19, progress in that research direction is at a standstill. Instead, other avenues of complementary research are being pursued in terms of astrochemical modeling, quantum chemical calculations and developing a more user-friendly graphical user interface for future data acquisitions.

4th report

The first publications relevant to this project have now been published. The SOLEIL beamtime has been scheduled for March 21st. I will submit another beamtime proposal building on the C60 results that have now been published. In the coming winter I will take several personal development courses since work-related travel abroad is forbidden by the Leiden university. But I will schedule my secondment to FELIX early 2021 – in all likelihood January.

6th report

My publication output in 2020 has been steady with six published papers (two relevant to PAHs and fullerenes and three more relevant to astrochemistry) and it appears that it will continue in 2021 with several papers in the pipelines. I also have upcoming beamtimes scheduled and a FELIX secondment that will undoubtedly be interesting as well. I expect to obtain very interesting results on GRANDPAHs in a variety of experiments in 2021 with the hard preparatory work I put in in the year 2020.

7th report

The first four months of 2021 I have published two works. One on the phthalide pyrolysis, solving an old spectroscopic riddle on the pyrolysis breakdown on the benzyl radical (an important reaction intermediate in combustion of fossil fuels) and one on the absolute photoionization cross section of NH2, an important reaction intermediate in astrophysical and combustion media.

Final report

For the last few months of the project I have published one more article and submitted another one. One that deals with the characterization of CH2I, CHI and CI radicals, and one that reexamines the photoionization dynamics of the S2 diradical.

There are many works currently underway. Three publications on results from i-POP, a follow up publication to my paper on C60 photoionization, and a few other photoionization papers on astronomically relevant molecules.  From the FELIX secondment there are two papers in preparation, one on perchlorinated PAHs and one on alkylated PAHs. From the other FELIX project there is another paper in preparation focusing on the single- and double hydrogen loss of anthracene and phenanthrene.